## Task List
Task List | Estimated Hours | Remarks
Synchronization of the admin dashboard to show the progress of whole webapp both from staff and client. 1. Stat for Total Allocated Staff. 2. Stat for Total Campaigns. 3. Stat for Total Circulations. 4. Stat for Total Likes. 5. Stat for Total Page Views. 6. Stat for Total Circulations Completed. 7. Stat for Total Additional Circulations. 8. Recent Campaigns. 9. Recently Allocated Staff. 10. Will check the graph implementation. 11. Sort the list of recent campaigns | 12 Hours
Proper implementation of downloading CSV file . 1. In client Dashboard 2. In staff Dashboard 3. In Admin Dashboard | 2 Hours
Member Listing Page in the admin dashboard has bugs in it . Following are the bugs that needs to be resolved on priority: 1. Adding a member the form won’t show all the fields for registration. Both for client and staff. 2. Sorting of the member listing . 3. Edit User won’t show proper prefilled information 4. Pagination for member listing , if the large amount of data needs to be shown. | 6 Hours
In allocation page when we click on staff preview it won’t show any details . It appear with empty info for the staff which is weird, so need to populate this page | 2 Hours | Please address what information of the staff need to be shown
Need to make the social link work. 1. Share with facebook 2. Share with twitter 3. Share with linkedin | 6 Hours
Success/Failure messages in a proper way on whole web app. | 5 Hours
Validation messages improvement on whole web app | 6 hours
On view campaign implement the slider functionality , where the user will hover on the cover image and then on hover sidebar will appear and will see the uploaded video and youtube video and if he clicks one of them it will scroll to that slide. | 6 hours
Login Attempts, to stop the brute force hacking . | 6 hours
New field in the admin panel to select the size & color for heading in the slider. | 2 Hours
Restrict form submission if pincode not entered. | 1 Hour
Mention if campaign has been ended or running in the campaign list. | 30 mins
Show proper address format | 30 mins
Total Hours | 59 Hours

## Design Tasks
Task List | Remarks
3 dots to represent number of sliders.
Copyright message in the login page
Set limit for heading and description in the slider | Please tell us the word limit for heading and description in the slider
Display contact info if user doesn’t get any mail for forget password and register. | Let us know what details should we display there.
Logo in forgot password
Text change in registration pages
* on every form
Character limit for description field | let us know the limit.