## IOS Testing
TEST CASE: GRANTED IOS Application
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| GRANTED TEST IOS APPLICATION | HIGH | TEST 002 | TEST 001 | 26/7/2020 |  | LOW
|  |  |  | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
|  |  |  | Haroun | 26/7/2020 |  | HIGH
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Splash Screen |  |  | Make the splash page only the colored image as agreed, no need anymore for the animation. | Fail
2 | Privacy Policy |  | It shoud load the page with the correct content when I click on it from the login/register page | It still loads extremely slow and the content is lorem ipsum. Make it's loading speed much faster, it is only a text page. I will also send you the privacy policy document to upload | Fail
3 | Terms of Service |  | It shoud load the page with the correct content when I click on it from the login/register page | It still loads extremely slow and the content is lorem ipsum. Make it's loading speed much faster, it is only a text page. | Fail
4 | Welcome to Granted Screen |  |  | - There is a spelling mistake that needs to be corrected at the bottom in the sentence "yoy re" | Fail
5 | Welcome to Granted Screen: Login/Register via Instagram |  | I should be able to login/register via instagram | When I click on instagram it asks me to login to my instagram account, which I do then it keeps loading forever. I close the app and reopen it and click on instagram againa and it only shows me a loading screen | Fail
6 | Welcome to Granted Screen: Login/Register via Facebook |  | I should be able to login/register via Facebook | When I click on Facebook it asks me to login to my facbook account, which I do then it displays an error that says "App Not Setup: This app is still in development mode, and you don't have access to it. Switch to a registered test user or ask an app admin for permissions". Send me the steps to send you our Application Facebook keys and the steps to activate the account so that it is not on test mode. | Fail
7 | Welcome to Granted Screen: Login/Register via Gmail |  | I should be able to login/register via Gmail | IT works correcty when I register for the first time. However, after I login, it directs me immediately to the homepage without first taking me to the different registration screens of Complete Profile and Choose your Preferences screens. This should only happen during registraiton only for the first time. Also when i register, it doesn't autofill my info from google like full name, gender, date of birth, phone. It should be even autofilled in the complete profile screen. Also, send us the guidlines how to setup the keys to authenticate via gmail to set it up under our account and give it to you | Fail
8 | Welcome to Granted Screen: Login/Register via Apple Signin |  | I should be able to login/register via Appe sign in as per their new guidelines | The icon is not even there in the app, add it as a circular icon next to the other three social media icons | Fail
9 | Forget Password Screen |  | I should be able to reset my password for an exisitng user account | You changed completely the functionality of the reset password. It is not the same as the mockups at all, where did you get the otp requirement? The process is simple, first I enter my email, if the email doesn’t exist the message should say "Opps, it seems there is no account registered with this email." If the email exists then you send a link to the email where the client will click on this link which will open the screen of the reset password to fill the two fields of the new password and once the reset is completed it should log the customer in automatically, send an email that his password was changed successfully as well as a push notification. | Fail
10 | Complete Profile Screen |  | Validations and designs should be as per the mockups | - First name and last name are minimum of 2 characters and a maximum of 20 characters - Date of birth, users below 18 years old can't use the application, so you should display this an an error - Telephone numbers can only be 8 numbers if I choose qatar. exactly 8 numbers, no less no more. Also, numbers should only start with either (5,6,7,3). for other countries no need for validation as long as it is a number - The page is allowing me to scroll slightly even though every field is showing - In Update profile under account, - When a profile is updated, no need for the popup success, just take them back to the previous screen automatically. | Fail
11 | My Profie: Upoading a proile image |  | I shoud be able to upoad a new image for my profile. | - If I signup using facebook, instagram or gmail, it should take the profile image from there. - When I upload a picture, it allows me to crop, however the scrolling vertically when cropping doesn’t work, it stays fixed. - When I upload an image and click use image, it should be updated automatically and not wait for me to click on save. - If i dont have a profile image and im in the my account screen and i click on the defualt avatar, it should allow me to upload a new image without clicking on personal information. | Fail
12 | Home Screen: Customer View |  | I shoud be able to see top rate, then the categories I have set as my preference, then the rest of all the categories | It only show top rated and my selected categories without seeing all the rest of the categories. Also new to granted slider doesn’t show. | Fail
13 | My Account: Change Password |  | If I logged in using facebook, instagram, gmail or apple, it shouldn't ask me for my current passwored | - It asks me now for my current password eventhough I registered via gmail. - I entered the same password for current and new passwords and it said it was changed successfully. It should ask me to enter a different password | Fail
14 | Invite your Friends |  | I Should be able to generate a special referal link and when sent, either it opens the app for the receiver of the link or I they don’t have the app instaled then it opens the page for ios/android app to download | It doesn’t work. The link only opens the app, but majority of people wont have the app beforehand | Fail
15 | Give us feedback screen |  | It should submit the feedback | Change the success message to "Thank you for your valuable feedback" | Pass
16 | Enjoying Granted Popup Screen |  | After the first video request completed successfully for a customer, prompt a popup to rate our application either on Apple Store or Playstore | I was not able to find this at all in the app | Fail
17 | Notifications page |  | If a notification is more than four lines, don’t display the rest of the lines and add show more | - Currently if I send from admin a push notification of for example 20 lines, it will show it all in a very long manner, we need to show only four lines and if more it will end in … show more which will collapse or expand the text - For the notification when i submit a request, when i click on it, it should take me to the page of this request. | Fail
18 | Search Screen |  | I should be able to search for a celebrity even though they are not assigned to my preferred categories or search a category | - I should be able to search using celebrity name, categories/subcategories or even using description of celebrity - While im typing the search query, the results should be updating automatically - If there are no search results, display a message that says "Sorry, no results found. Try a different keyword" - After searching for something, i want to clear my search so i click on the close icon, it removes the text but i have to click on it again to reset the page completely | Fail
19 | Discover Granted Screen |  | Not only show timeline videos, but also the profile video of a celebrity who just joined as well as videos submitted by a celebrity to a fan as long as the video is marked as public | - When a new celebrity joins the app, display their profile video here - When any video is submitted by a celebrity to a fan, add it here unless the customer marks it private - The celebrities image doesn’t show even though it shows correctly on ios | Fail
20 | All App Videos |  | Videos should be extremely fast to load and play as well as with the correct dimensions/resolutions | - All videos are very very very slow. This is top priority to fix where the app must be extremely fast to load videos - Make all videos full height and if the video was shot in portrait mode, its fine to have black space on the left and the right as long as the full height is shown and that the video is not cropped or compresses or stretched | Fail | This is top priority now.
21 | Book a Celebrity |  | Everything should be working and designed as per the design mockups | - Make the background a bit darker/less transparent as per the mockup - when I scroll down, the celebrity image remain as it is fixed and goes over the fileds. Keep it fixed but add a bit of white space under it so the image doesn’t go over th fields - Under Request type, above Anniversary, there is a big white space that needs to be removed and increase the height of the dropdown screen opetions - When i enter one character in the instructions field, the app crashes. The minimum should be 10 characters. - Thier name under the booking for someone else, should be minimum 3 characters - THere is a big white space under the record part that needs to be removed | Fail
22 | Login to a Gmail account that was already registered |  | It should log me in no issues | Even though I completed my profile, it deleted everything I added and sent me a push notification to complete my profile!! | Fail
23 | Try to book a video when I didn’t complete my profile |  | IT should prompot a popup saying that I need to first complete my profile with a button to do that | IT just says "Error: Please complete your profile". Instead of this, open automatically the complete profile screen to be filled first and when it is filled take them aterwards automatically to the book screen without the preference screen. | Fail
24 | General Comment: Slide up to refresh |  |  | when I slide my finger down at the top of the page, it should refresh the page and update any info. This to be in the whole app | Fail
25 | Failed Payment |  | When a payment fails, you need to display the actual error message while still staying at the card screen from tap | When a payment fails, you need to display the actual error message while still staying at the card screen from tap | Fail
26 | Successful Payment |  | When a payment is successful, it should reserve the amount and not capture it until the video is submited | I can't get any payment to work, it keeps saying failed eventhough I tried the card you gave. It also takes too long to load. In adroid it is giving me error "auth_TS0730202C 1336w7L32607526". Not a single transaction is showing in the dashboard of tap, I checked with tap they said you have to make an api request to verify the status of the payment. SO we will have to demo this together after you fix the payment | Fail
27 | Successful Payment |  |  | - I initially filled all details for someone else, then switched to myself, when the booking was done, I found out it went with someone else and not my last choice | Fail
28 | My Videos: Empty |  | It should say that there are no messages with the discover button as per the mockup | The page is completely empty, make sure it is exactly as per the mockup | Fail
29 | My Videos |  |  | - the line under each different request is touching the screen from the right side, it needs to be the same length and weigth and color as per the mockups. | Fail
30 | Recording Video as celebrity |  | The functionalities and design should show as per the mockups | - When I record a video as a celebrity, there is a gray space above and under the my camera, it needs to be full height - When I upload from gallery, and the video is a square, it adds a big gray space above and under the video which is fine, but make it black. - Uploading a video is still extremely slow, needs to be very very quick - When i flip the camera, the view doest change to horizontal | Fail
31 | Video Request completed: Customer |  | I should receive a notification when the video is completed and see the details of the video | - I receive two notifications that the celebrity accepted my request then another one that the video was sent. Don't send both after the video request is finalized by the celebrity, remove the notification about celebrity accepting the request. - when a reaction is submitted, the message should be "Thank you, we will let @celebrity know your reaction" - By default make the video public unless the customer chose to mark it as private - when i like a video, no need for popup to confirm | Fail
32 | Lazy Loader |  |  | Make the lazy loader as the lazy loader in admin page | Fail
33 | Share a video as a customer |  |  | - You are displaying the link of the admin panel which is very very bad from a security standpoint. We need to keep it under granted.me domain or have it as a masked link. - Also when the shared video is sent, you should send the link of the video where the video plays as before, now it only downloads automatically (i tried with .mov format) | Fail
34 | Celebrity: Granted Icon |  | When I click on the granted icon from the celebrity app, it should take me to the screen of edit profile | need to be correct as you are taking the celebrity to the page of view profile only,not the edit page | Fail
35 | Celebrity: Home Screen |  |  | - Instead of pending amount, change it to "Profit". Also the amount should be after deducted from the money the admin commission | Fail
36 | Save Login details in app |  | When I enter an account, apple should be able to recognize and save the details. | Nothing happens, when I logout and try to login, I have to type everything again | Fail
37 | Banking Info |  | I should be able to add a bank account and then delete it or edit it later | I can't edit when I click on it. | Fail
38 | Edit Bank Info |  |  | You are dispaying both back button and close button, you need to design it as per the mockups | Fail
39 | Deleting a reported video |  | It shouldn't show anywhere in the app for celebrity or customer | After deleting a reported video, it was still showing and I was able to click on it and play the video. The video should be replaced with a text "Video has been reported and removed." | Fail
Old Bugs not fixed
40 | Sign up Screen |  |  | The password policy should only be minimum 8 characters, and contact letters (small or capital) and numbers | Pass | The bar under the signup button is too big and almost touching the button text; needs fixing. No registration email!
41 | Home Screen Categories |  |  | The first section should show top rated, then show in alphabetical order the preferred categories selected by customer then the rest of all sub categories followed | Fail
42 | All system generated emails to be sent via smtp |  |  | Nothing is being sent | Fail
43 | Profile Screen: Notifications |  |  | by default turn off phone calls and text messages | Fail
44 | Profile Screen: Help Inquiries and Feedback |  |  | It works and is showing correctly in Admin. However, there should be a button when I open the inquiry to send a push notification or email to that customer. Also it is called Give us feedback not get us feedback. Make sure the wording is exactly as given in the mockups | Fail | When I submit an inquiry, it should be written in the notifications page but not clickable
45 | Booking Confirmation Notification screen |  | When I click on it, it should take me to the booking confirmation page. | Nothing Happens when I click | Fail
46 | Celebrity First Login |  |  | I can't click skip | Fail
47 | Celebrity Notification: New Request |  |  | When I click on the push notification of the new request, it should open this request, not the home screen
48 | Celebrity Sends a video |  |  | When a celebrity sends a video, the customer receives two notifications that the request was accepted and that the video is sent, the order should be accepted first then video |  | When I click on push notification, it should open the video automatically
49 | Login Popup |  | When I enter my login details correct, it should log me in automatically without any popup for success | I have to click ok to be logged in. Remove this popup
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272

## Android Testing
TEST CASE: GRANTED Android Application
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| GRANTED TEST Android APPLICATION | HIGH | TEST 002 | TEST 001 | 26/7/2020 |  | LOW
|  |  |  | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
|  |  |  | Haroun | 26/7/2020 |  | HIGH
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Status Bar |  | Items in the phone status bar should be in black | Currently everything is showing in white and nothing is visible | Fail
2 | Signup Via Email |  | When I register via email with a new email that doesn’t exist it should allow me to login | I entered twice two diferent emails that im sure are not in the database and it gives me an error that the email already exists but then it sends me a push notification welcome to granted and creates the customer in admin. | Fail
3 | Welcome to Granted Screen: Login/Register via Instagram |  | I should be able to login/register via instagram | When I click on instagram it keeps the page empty for sometime then gives me error Web page not available with net::ERR_TIMED_OUT | Fail
4 | Welcome to Granted Screen: Login/Register via Facebook |  | I should be able to login/register via Facebook | When I click on Facebook it displays an error that says "App Not Setup: This app is still in development mode, and you don't have access to it. Switch to a registered test user or ask an app admin for permissions". Send me the steps to send you our Application Facebook keys and the steps to activate the account so that it is not on test mode. | Fail
5 | Welcome to Granted Screen: Login/Register via Gmail |  | I should be able to login/register via Gmail | First time I clicked on login via gmail, it logged me in automatically to one of the gmail accounts without asking me to choose which email to choose from. I had to logout and click on the gmail icon to finally be able to select which gmail account i want to use. IT works correcty when I register for the first time. However, after I login, it directs me immediately to the homepage without first taking me to the different registration screens of Complete Profile and Choose your Preferences screens. This should only happen during registraiton only for the first time. Also when i register, it doesn't autofill my info from google like full name, gender, date of birth, phone. It should be even autofilled in the complete profile screen. Also, send us the guidlines how to setup the keys to authenticate via gmail to set it up under our account and give it to you | Fail
6 | Forget Password Screen |  | I should be able to reset my password for an exisitng user account | When i click on forget password and enter my email, it takes for ever to load; and it doesnt work at all. if the email doesn’t exist the message should say "Opps, it seems there is no account registered with this email." If the email exists then you send a link to the email where the client will click on this link which will open the screen of the reset password to fill the two fields of the new password and once the reset is completed it should log the customer in automatically, send an email that his password was changed successfully as well as a push notification. | Fail
7 | My Profie: Upoading a proile image |  | I shoud be able to upoad a new image for my profile. | - If I signup using facebook, instagram or gmail, it should take the profile image from there. - When I upload a picture, it allows me to crop, however the scrolling vertically when cropping doesn’t work, it stays fixed. - When I upload an image and click use image, it should be updated automatically and not wait for me to click on save. - If i dont have a profile image and im in the my account screen and i click on the defualt avatar, it should allow me to upload a new image without clicking on personal information. | Fail
8 | Home Screen: Customer View |  | I shoud be able to see top rate, then the categories I have set as my preference, then the rest of all the categories | It only show top rated and my selected categories without seeing all the rest of the categories. Also new to granted slider doesn’t show. | Fail
9 | Notification Page |  | As per the mockup in terms of design and functionalities | - The buttons like view or complete are not rounded boxes like the mockup and are under the text and not on the same line - The welcome notification should have the customer name as per the mockup, so it should be "Welcome to Granted, Tamer" - When click on the three dots, the buttons of mark all as read and cancel are small, it needs to be the wider as per the mockup. Also the title should be "My Notifications" Not my alerts - When i mark all as read, no need to display any success messages for me - I sent a very long push notification from admin and i didnt get the alert on my phone at all, even though when i opened the app the notification was there - Currently if I send from admin a push notification of for example 20 lines, it will show it all in a very long manner, we need to show only four lines and if more it will end in … show more which will collapse or expand the text - For the notification when i submit a request, when i click on it, it should take me to the page of this request. | Fail
10 | Complete Profile Screen |  |  | - Search for country code doesn’t actually work when I search for a country after clicking on the phone code - First name and last name are minimum of 2 characters and a maximum of 20 characters - Date of birth, users below 18 years old can't use the application, so you should display this an an error - Telephone numbers can only be 8 numbers if I choose qatar. exactly 8 numbers, no less no more. Also, numbers should only start with either (5,6,7,3). for other countries no need for validation as long as it is a number - For Nationality, the country search is also not working - Under update account, - When a profile is updated, no need for the popup success, just take them back to the previous screen automatically. | Fail
11 | My Account: Change Password |  | If I logged in using facebook, instagram, gmail or apple, it shouldn't ask me for my current passwored | - I entered the same password for current and new passwords and it said it was changed successfully. It should ask me to enter a different password | Fail
12 | Invite your Friends |  | I Should be able to generate a special referal link and when sent, either it opens the app for the receiver of the link or I they don’t have the app instaled then it opens the page for ios/android app to download | It doesn’t work. The link only opens the app, but majority of people wont have the app beforehand | Fail
13 | Give us feedback screen |  | It should submit the feedback | Change the success message to "Thank you for your valuable feedback" | Pass
14 | Enjoying Granted Popup Screen |  | After the first video request completed successfully for a customer, prompt a popup to rate our application either on Apple Store or Playstore | I was not able to find this at all in the app | Fail
15 | Home Screen: Customer View |  | I shoud be able to see top rate, then the categories I have set as my preference, then the rest of all the categories | - It only show top rated and my selected categories without seeing all the rest of the categories. Also new to granted slider doesn’t show correctly - the titles of each category and the name of the celebrity are not the same font weight, make sure everything is identica to the mockups - Add space between See all and (98) - The search icon is lighter in weight than the mockups | Fail
16 | Search Screen |  | I should be able to search for a celebrity even though they are not assigned to my preferred categories or search a category | - I should be able to search using celebrity name, categories/subcategories or even using description of celebrity - While im typing the search query, the results should be updating automatically - If there are no search results, display a message that says "Sorry, no results found. Try a different keyword" in bold letters | Fail
17 | All App Videos |  | Videos should be extremely fast to load and play as well as with the correct dimensions/resolutions | - All videos are very very very slow. This is top priority to fix where the app must be extremely fast to load videos - Make all videos full height and if the video was shot in portrait mode, its fine to have black space on the left and the right as long as the full height is shown and that the video is not cropped or compresses or stretched | Fail | This is top priority now.
18 | Celebrity Screen |  | It should be the same design and functionalities as per the mockup | - Icons are super small like the share and the sound - The height of the video is too short, it needs to be longer as per the mockup - Most of the font weights in this page are wrong size or weight, check and correct it as well as for the whole app - When i share, you are displaying the link of the admin panel which is very very bad from a security standpoint. We need to keep it under granted.me domain or have it as a masked link. - Also when the shared video is sent, you should send the link of the video where the video plays as before, now it only downloads automatically. | Fail
19 | Lazy Loader |  |  | Make the lazy loader as the lazy loader in admin page | Fail
20 | Login Popup |  | When I enter my login details correct, it should log me in automatically without any popup for success | I have to click ok to be logged in. Remove this popup | Fail
21 | Privacy Policy |  | It shoud load the page with the correct content when I click on it from the login/register page | It still loads extremely slow and the content is lorem ipsum. Make it's loading speed much faster, it is only a text page. I will also send you the privacy policy document to upload | Fail
22 | Terms of Service |  | It shoud load the page with the correct content when I click on it from the login/register page | It still loads extremely slow and the content is lorem ipsum. Make it's loading speed much faster, it is only a text page. | Fail
23 | Welcome to Granted Screen |  |  | - There is a spelling mistake that needs to be corrected at the bottom in the sentence "you re" where you are missing the ' | Fail
24 | Book a Celebrity |  | Everything should be working and designed as per the design mockups | - As per the mockup, you need to add a black semi transparent background covering the celebrity page behind the booking screen. You should stop the celebrity video from playing. - Remove --Request Type-- under the request type, it should only be a text place holder, not an actual entry - when I scroll down, the celebrity image remain as it is fixed and goes over the fileds. Keep it fixed but add a bit of white space under it so the image doesn’t go over th fields - When i enter one character in the instructions field, the app allows me. The minimum should be 10 characters. - Thier name under the booking for someone else, should be minimum 3 characters | Fail
25 | Successful Payment |  |  | - I initially filled all details for someone else, then switched to myself, when the booking was done, I found out it went with someone else and not my last choice - When the payment is successful, it shows a short popup at the top with authorization code, this shouldn't show to customers | Fail
26 | My Videos |  |  | - There are no lines as per the mockups above statuses, under statuses and under each celebrity - under pending, add a space between pending and between - and between 7 days left - The statuses (Pending, competed, cancelled, all) Are not full width as per the mockupm there is a big space after all. - Only the status tap im on should be in bold not all as per the mockup - In the celebrity app, the statuses are repeated twice | Fail
27 | Celebrity My Progress Screen |  |  | - There are no gray lines above weekly or under them - When I click on the pending requests it doesn’t take me to the pending tap under my videos - The chart is not the same design as the mockups - the fonts in this page is very different from the mockups, it needs to be identical - Chance Pending Amount to Profit. Also the amount should be after deducted from the money the admin commission
28 | Decline video |  |  | The popup is very bad, why is it not designed well?
29 | Recording Video as celebrity |  | The functionalities and design should show as per the mockups | - When I record a video as a celebrity, there is a black space above and under the my camera, it needs to be full height - After i record a video and click on the close icon on the top left, it should remove the video but keep me in the camera view - When I upload from gallery, and the video is a square, it adds a big gray space above and under the video which is fine, but make it black. - Uploading a video is still extremely slow, needs to be very very quick - When i flip the camera, the view doest change to horizontal - There is no option to download after recording the video as per the mockup | Fail
30 | Video Page: Celebrity View |  |  | Everything in this page needs to be redesigned to match the design mockups | Fail
31 | Video Request completed: Customer |  | I should receive a notification when the video is completed and see the details of the video | - I receive two notifications that the celebrity accepted my request then another one that the video was sent. Don't send both after the video request is finalized by the celebrity, remove the notification about celebrity accepting the request. - when a reaction is submitted, the message should be "Thank you, we will let @celebrity know your reaction" - By default make the video public unless the customer chose to mark it as private - when i like a video, no need for popup to confirm - The popup to submit a feedback or report needs to be designed - When i click on the three dots in the top right corner, you need to make them full width | Fail
32 | Share a video as a customer |  |  | - You are displaying the link of the admin panel which is very very bad from a security standpoint. We need to keep it under granted.me domain or have it as a masked link. | Fail
33 | Celebrity: Granted Icon |  | When I click on the granted icon from the celebrity app, it should take me to the screen of edit profile | need to be correct as you are taking the celebrity to the page of view profile only,not the edit page | Fail
34 | Banking Info |  | I should be able to add a bank account and then delete it or edit it later | I can't edit when I click on it. | Fail
35 | Edit Bank Info |  |  | You are dispaying both back button and close button, you need to design it as per the mockups | Fail
36 | Deleting a reported video |  | It shouldn't show anywhere in the app for celebrity or customer | After deleting a reported video, it was still showing and I was able to click on it and play the video. The video should be replaced with a text "Video has been reported and removed." | Fail
Old Bugs not fixed
37 | Sign up Screen | 2020-12-07 |  | Design wise its cool, when sign up manaully with email and pass is fine | Pass | We didnt get an email when signed up
38 | Complete Profile Screen | 2020-12-07 |  | Complete profile screen Crashed when i was messing around with the date page when i opened the app again it skipped the profile screen and went directly to home. When keyboard is out on name field and you choose date of birth without removing keyboard date menu comes over keyboard https://drive.google.com/file/d/1ynIHnvCSRanymWCTUw6YfyIpHcawTVdj/view?usp=sharing And the date of birth should be until current year Not 2082 in the future how is that possible Show user that he can actually change or add profile picture as their is no indication until its clicked. Photo asked for permission then nothin happened needed to click on profile pic again to get choices where i will take pic from on mobile Categories at the bottom of the profile screen makes no sense being at the bottom | Fail
39 | Profile Screen: Change Password | 2020-12-07 |  | When signed in via social media and want to change password you have to enter your current password?? and did not receive a password change email/notification | Fail
40 | Celebrity Screen: Design | 2020-12-07 |  | Talent Profile vidoes are in the wrong dimension it should be portrait and not landscape. From talent app on android after recording it keeps asking for to record vidoe when we already did. | Fail
41 | Celebrity Screen: Best Videos | 2020-12-07 |  | Loading takes forever -- still slow | Fail
42 | Celebrity Screen: Profile Video | 2020-12-07 |  | Talent Profile vidoes are in the wrong dimension it should be portrait and not landscape. From talent app on android after recording it keeps asking for to record vidoe when we already did. | Fail
43 | Booking Screen: Background | 2020-12-07 |  | The problem is the layers of pages on top of each other and A very tiny Profile pic is very useless https://drive.google.com/file/d/1rTXACe6w2mVo3vV-o9qcajWRtWBSYHja/view?usp=sharing | Fail
44 | Booking Screen: Someone Else | 2020-12-07 |  | Videos are play for some reson on the background of the booking screen Back button on top left of screen no working need to go back with mobile button or gesture. When booked video notification came when clicked on it, it took me to splash screen and then home page. | Fail
45 | Booking Confirmation | 2020-12-07 | When a booking is placed successfully, it should autmatically take you to the booking confirmation page with the push notification, no need for the popup | When booked it didnt take me to booking page and also when clicked on alert it just marked it as unread and no action took place. Back button on top right didnt work Works fine however | Fail
46 | Booking Confirmation Screen | 2020-12-07 |  | When booked it didnt take me to booking page and also when clicked on alert it just marked it as unread and no action took place. Back button on top right didnt work Works fine however | Fail
47 | Booking Confirmation Notification screen | 2020-12-07 | When I click on it, it should take me to the booking confirmation page. | When booked it didnt take me to booking page and also when clicked on alert it just marked it as unread and no action took place. Back button on top right didnt work Works fine however | Fail
48 | Booking Admin Page | 2020-12-07 |  | Booking on admin and admin page loves opening in new tab we need to reduce that Also the information showing on table mode doesnt show in view more details which is weird | Fail
49 | Customer Share Video | 2020-12-07 |  | The video is shared, however the link that is sent needs to be changed as it shows, the admin panel URL | Fail
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278

## Admin Testing
TEST CASE: GRANTED IOS Application
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| GRANTED TEST IOS APPLICATION | HIGH | TEST 001 | TEST 001 | 2020-11-07 |  | LOW
|  |  |  | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
|  |  |  | Haroun | 2020-11-07 |  | HIGH
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | When a user registers, I need to be able to see how did he registered. |  | When a user registers, I need to be able to see how did he registered. Be it via email or instagram or facebook or Gmail or apple account | I can't find out this information
2 | To be able to see login logs of user |  | When I click on a user in admin, I should be able to see their login logs as in barber admin | I can't find out this information
3 | When a user sumbits a help query and the admin sends an email or push notification |  |  | - I need to see if the user ready the push notification or not - I Need to have the option send a message to the user as both email and push notification - When admin change the status of a hep query to closed or resolved, send an automated email and push notification that says "Dear valued customer, your query has been marked as resolved."
4 | Manage Categories |  | I should be able to see all active/inactive categories, update and filter as well as see celebrities associated with a specific category | - Add filters to be able to filter for active/inactive - Add a filter to filter categories from sub categories - When I click on any of the columns to sort, it doesn’t work, only the sorting arrow changes from up to down - Under a category display all celebrities under this category with ability to remove or add celebrities to this category page directly.
5 | Manage what shows on Discover Granted page |  | I should be able to turn on and off the below: - show celebrities when they join - show celebrities timeline videos - show celebrities fan videos as long as they are marked as public |  |  | Make sure if a video is reported that it doesn't show at all in discover or any other page, only in admin
6 | All Search Records Screen |  | IT shoud collect search queries done by users | The below needs to be corrected: - there should be a tap where the queries are grouped, so it will show the query text and the number of people who searched for it - If a guest made the search, put the name as Guest not a -
7 | Manage Bookings: Transaction Details |  | IT should ope the details of the transaction | Clicking on transaction details for order 297 crashes the admin page
8 | Admin Timezone |  |  | It should be the time zone of Qatar, I tried to make a booking and the time was off by around 3 hours
9 | Change of Commission |  | I should be able as an admin to change the commission to a fixed price and change that price or make it a percentage. | Right now there is no option for percentage even though we are starting with 25%
10 | View Celebrities |  |  | - I should be able to see the total number of money made for each celebrity, the total commission I made from him/her so far, and number of current pending, competed and cancelled requests
11 | Booking Completed |  |  | I need to be able to see if the video is public or private and change that as an admin
12 | Email SMTP |  | Should be editable from admin | I added the correct smtp details and tried to send a promo email but it gave me the below error: Failed to authenticate on SMTP server with username "hello@granted.me" using 2 possible authenticators. Authenticator LOGIN returned Expected response code 235 but got code "535", with message "535 5.7.3 Authentication unsuccessful [CO2PR04CA0196.namprd04.prod.outlook.com] ". Authenticator XOAUTH2 returned Expected response code 235 but got code "535", with message "535 5.7.3 Authentication unsuccessful [CO2PR04CA0196.namprd04.prod.outlook.com] ".
13 | Admin: Create Celebrity (passowrd) |  |  | In the password field there should be two buttons, one to generate password and one for copying the password. The password should contain capital and small letters as well as numbers so it doesn’t give them errors when logging in
14 | Admin Celebrity Page |  |  | - I should be able to add a bank account details on behalf of the celebrity - I should have a tap called settlements under each celebrity generated at the end of each month with how many videos they made, the amount we need to pay them and our commission from them for this month. This will help us know how much money to send them at the end of each month. As discussed earlier each settlement will have a status where once it is changed to done by admin it will send a push notification to the celebrity that his money for this month has been sent to his bank account
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267